## Sheet1
PROJECT | PRIORITY LEVEL | DESCRIPTION | Status
2020 BUDGET | HIGH | Preparing Budget for Discussion | COMPLETE
MASTER PLAN | HIGH | Update the Master Plan / Separate from Joint Master Plan | 2020
PARKS & RECREATION PLAN | HIGH | Sub-committee continues to update P&R Plan. | IN PROGRESS
PARKS & REC ORDINANCE | HIGH | Using sub-committee of the PC to review plan. P&R Ordinance initiative retracted. | INITIATIVE RETRACTED
VEHICLE PURCHASE | HIGH | Utility vehicle is now in service. | COMPLETE
VEHICLE PURCHASE #2 | HIGH | Ford Fleet # applied for as required for discounted rate. UPDATE: 11-12-19 Purchase Agreement being drafted for consideration. New vendor being utilized / former vendor no longer being used. | IN PROGRESS
DIRECTOR OF FACILITIES | HIGH | A position that is a high priority for Village Council - Advertised in MWEA / MML- Hired. | COMPLETE
BEACH STREET PUMPS | HIGH | This item has gone from a medium/low priority to High priority due to a pump failure. Cost before VC for consideration to purchase 2 new pumps and one set of VFD's. UPDATE: Upon discussion with electrician VFD is readily available. No purchase of VFD was made. Update: Pump drawdown test mid-July data stored. Cost of pumps came from funds previously allocated to canceled project. | COMPLETE
CROSS CONNECTION ORDINANCE | HIGH | MDEQ REQUIREMENT | F&V
LEAD & COPPER MATERIALS INVENTORY | HIGH | MDEQ REQUIREMENT - PRELIMINARY DISTRIBUTION SYSTEM MATERIALS INVENTORY (DSMI) DUE JANUARY 1, 2020 | COMPLETE
PORT SUTTONS LIFT STATION | HIGH | Construct new lift station to service PS and Bay View. Bids Received cost too high at $568,000 with $350,000 budgeted. UPDATE:- Cancelled project due to lack of need. | PROJECT CANCELED
EMPLOYEES MANUAL | HIGH | Proposal before VC 9-16-19. UPDATE: 11-21-19 Rough Draft Received. | IN PROGRESS
TAP GRANT - DETOUR AMENDMENT | HIGH | Change TAP grant detour to 4th street update- Postponed following Pre-con meeting. | COMPLETE
MARINA - EMERGENCY REPAIRS | HIGH | High water erosion issues. - Meeting with the Engineer and State on 6-10-19 - UPDATE: requires additional permitting per Robyn. F&V working on this. UPDATE: Permit Received. | COMPLETE
CONSUMERS CONTRACTS | HIGH | Are resolutions needed? UPDATE: to be discussed at September Utility Committee Meeting. | IDLE
CROSS CONNECTION TRAINING | HIGH | Staff Training Required | IDLE
WWTP - LINER & BAFFLE REPLACEMENT | HIGH | Maintenance Item ordered as a cost savings to replace baffles during liner replacement. | COMPLETE
PUBLIC / MARINA RESTROOM UPGRADES | HIGH | The structure appears to have or currently is settling causing structural damage. Engineer to evaluate the structures integrity and offer solutions. UPDATE: Engineer meeting scheduled for September 9th. | COMPLETE
BROADWAY ROAD DRAINAGE | HIGH | Drainage overflow from private property causing secondary issues. UPDATE: field visits confirm private basin is the issue causing down street erosion and possible flooding. Discussed with LCRC. UPDATE: LCRC was sent an email based on memo stating it was installed by the LCRC awaiting response. UPDATE: Verbal provided by LCRC superintendent with no memory or information, including plan sets for the road. UPDATE: 10-1-19 Searching permits at County level. UPDATE:10-7-19 Dave and I met with LCRC manager to discuss various items mostly collaboration. 11-22-19 Met with Drain Commissioner/SB Township Supervisor on issue. Drainage district proposed for consideration to fix lack of culverts, ditching. etc. Further research by DC forthcoming. | IN PROGRESS
FACILITIES PHONE UPGRADE | HIGH | Current phones dated and costly. New phones provided through government first responder initiative at less cost with benefits. | COMPLETE
MARINA PROJECT- Overall Project | HIGH | CONSTRUCTION PROGRESSING - BEHIND SCHEDULE - UPDATE- Walkthrough completed 7-16-19. UPDATE: Received an email with checklist of remaining items to be completed on 9-19-19. October 15 completion date. UPDATE: 10-29-19 - The Marina project is approximately 90% complete.UPDATE: 11-27-19 Met with engineer to finalize contract cost. | 90% COMPLETE
MARINA PROJECT - Weggener - Electrician | HIGH | UPDATE: 11-27-19 Met with Waggoner Electric to finalize contract overture cost. Deal negotiated - complete. | COMPLETE
MARINA PROJECT - Engineer | HIGH | UPDATE: 11-26-19 Met with project engineer to finalize contract overture. Deal negotiated | COMPLETE
MARINA SEICHE POND | HIGH | Met with Leelanau County Soil Erosion regarding new sand and ponding. Update - Met with Robyn (EGLE) regarding the seiche pond - Contacted the Army Corp regarding both. - Working with corp- Both County & EGLE have no issues. UPDATE: Topo in place. UPDATE: 4 dates provided in which the emergency manager, was contacted due to threats to our marina infrastructure.(7-22/7-23/7-25/7-29) | COMPLETE
WEBSITE | HIGH | ONGOING - Dorothy constructing site with assistance from LIAA.Website is up and running! | COMPLETE
TAP PROJECT | HIGH | Ongoing Discussions with Engineer / STATUS UNKNOWN - UPDATE - Walkthrough scheduled 7-17-19 UPDATE: Pre-con being scheduled. UPDATE: Postponed UPDATE: 11-25-19 - Still postponed until Spring. | POSTPONED
OFFICE ASSISTANCE | HIGH | A position that is a high priority. | COMPLETE
ARCHITECT - ADA COMPLIANT DECK | HIGH | Funding retracted by committee. All involved have been notified that project is a no go. | INITIATIVE RETRACTED
STREET EVALUATION SOUTH SHORE | HIGH | Evaluation of S. Shore "hump" has been requested. Apparently the hump is a result of a stream culvert? | 2020
VILLAGE STREET - WEIGHT LIMITS | HIGH | Vehicles with excess weight damaging Village Streets. Weight limits on numerous roadways including Elm to circumvent unnecessary weight and short cuts by semi-trucks. UPDATE: 9/19 Meeting scheduled with LCRC. | IDLE
STREET EVALUATION - ELM STREET | HIGH | STREET REPAIR TO BE EVALUATED. UPDATE: Meeting with LCRC 10-7-19 to discuss the roadway. A very good meeting with the manager. Looking forward to further collaboration on this item as well as others. Update: Village is not eligible for consideration for federal $$$ (Ruiral Task Force) until 2022-23. | IN PROGRESS
WATERWHEEL PARK | MEDIUM / HIGH | Creek restoration, waterwheel upgrade, wall replacement, etc. UPDATE: Ongoing conversations with Watershed Center - -No action as of yet - Seeking other avenues. UPDATE: Engineer review complete. Discussion on validity of bids received in 2018 needs discussion. | ENGINEER EVALUATION COMPLETE
PLANNING COMMISSION BY LAW UPDATE | MEDIUM / HIGH | Review and amend bylaws to understand roles & responsibilities, the reason they are on PC, why decisions are made and personal conduct. UPDATE; 10-2-19 Complete | COMPLETE
VILLAGE ATTIRE | MEDIUM / HIGH | All workers in the field to have logo's/uniforms. 11-22-19 Four recently purchased work jackets have been taken in for logos. More to come. | COMPLETE
PLOW TRUCK | MEDIUM / HIGH | Plow truck was taken in July -received in November. 11-20-19- Inspection of brakes showed maintenance neglect. Leaf spring broken badly needs replaced. | COMPLETE
VILLAGE HALL LANDSCAPE | MEDIUM / HIGH | A 2019 budgeted item with high importance to VC. UPDATE: 10-7-19 Contract signed irrigation/landscape to be installed within 3-4 weeks. UPDATE: 10-24-19 Complete/Winterized 10-25-19. | COMPLETE
MARINA BRIDGE REPLACEMENT | MEDIUM / HIGH | The bridge is increasingly becoming aged. Incorporate it into a CMG grant with shoreline protection. Discussed with Engineer and MDEQ - 6-5-19 | IDLE
WATER RESERVOIR EXPANSION | MEDIUM / HIGH | Per MDEQ additional water storage is REQUIRED - this item was recommended by the MDEQ in 2018. UPDATE: F&V reviewing financials and eligibility for granting opportunities. UPDATE: Met with F&V to discuss expansion initiative. 40 year loan @ 2.5%(ish) on $2.5 million loan would cover line upgrade northern loop, reservoir, and 2 new wells. Next steps forthcoming. See rate note below. | IN PROGRESS
WATER RATES | MEDIUM / HIGH | EVALUATION OF WATER RATES UPDATE: F&V UPDATE: Reviewing UPDATE: Met with F&V to discuss expansion initiative. RATES would see less than $4.00 / month increase for reservoir expansion etc. listed above to cover that project for life of loan. | IN PROGRESS
WATER LICENSE | MEDIUM / HIGH | Per MDEQ additional water license of S3 required in less than 150 users. This item has been recommended by the MDEQ in 2018, new hire is qualified. | COMPLETE
BLIGHT ORDINANCE | MEDIUM / HIGH | Pre-Draft provided to General Committee at the September 3rd meeting to determine support for the initiative. Recommendation was to move forward with close attention to ornament grass. UPDATE: 10-28-196 sent to the Attorney for review/comment. | IN PROGRESS
LAND DIVISION ORDINANCE | MEDIUM / HIGH | This Ordinance is antiquated and should be simplified. | IN PROGRESS
PRIVATE ROAD ORDINANCE | MEDIUM / HIGH | Standards in the zoning ordinance are antiquated and should be revised to allow flexibility and to regulate the roads by number of users rather than length. | IN PROGRESS
INLAND SEAS LEASE AGREEMENT | MEDIUM / HIGH | 6-6-19 provided comments in email following meeting / discussions with Inland Seas - UPDATE; INLAND SEAS TO HAVE ATTORNEY DRAFT A LEASE AGREEMENT. UPDATE: 11-21-19 Draft Lease agreement received, being reviewed for content and will provide comments on the lease. | IN PROGRESS
BROADBAND AVAILABILITY | MEDIUM / HIGH | GTB is running broadband to the Suttons Bay Schools and through the Village. Discussions on extending the Broadband to the Village Hall (and other municipalities) was positive. | IN PROGRESS
METRO ACT PERMIT | MEDIUM / HIGH | Went before the committee in September and was recommended for approval to VC September 16th. UPDATE: Permit issued and mailed to the State as required. | COMPLETE
DUESTER PARK UPGRADES | MEDIUM / HIGH | Clean out and reclaim restrooms. Paul did a great job leading the project and personally re-plumbed the bathrooms. | COMPLETE
NORTH PARK BATHROOM UPGRADE | MEDIUM / HIGH | Replace faucets with "timed" faucets and replace counters. Both faucets broken and counters rotted. | IN PROGRESS
MARINA - COAL DOCK | MEDIUM / HIGH | Armoring Coal Dock Side - Changes needed to plans to account for high water. - Permits issued - UPDATE: Move to 2020. UPDATE: Contract signed with Elmer's 10-23-19 to move forward with Fall 2019 project. | COMPLETE
PORT SUTTONS GENERATORS | MEDIUM / HIGH | Quotes received for permanent generators. Budget allows for purchase. Generators will supplement (1) Lift Station & (1) Water well house. UPDATE: 9-19 Funding in place to purchase prior to the budget year. UPDATE - Signed purchase agreement 11-20-19. Awaiting installation, typically a 60-90 day timeframe. | COMPLETE
WATER WELL PROTECTION PROGRAM | MEDIUM / HIGH | Recommended by MDEQ to update / redraft well protection - This item has been recommended by the MDEQ in 2018 UPDATE: 10-08-19 We received notice today that our grant application was accepted by EGLE. Formal paperwork forthcoming. | IN PROGRESS
VILLAGE WATER ORDINANCE | MEDIUM / HIGH | This item has been recommended by the MDEQ in 2018 - Ordinance dated needs attention - F&V to review and provide direction. Contract needed | INITIATED
WATER ORDINANCE INTERPRETATION | MEDIUM / HIGH | Amend ordinance to incorporate interpretation / policy approved by VC. UPDATE - Engineer review prior to amendment. UPDATE: Policy/interpretation rescinded 7-15-19 VC Mtg. | COMPLETE
VILLAGE LOGO | MEDIUM / HIGH | New logo that better fits the Village. | COMPLETE
GPS SERVICES | MEDIUM | There have been several discussion with the vendor working towards a free 30-60 day unit and service. - Wil meet in fall to continue discussions. - UPDATE: Trial period accepted by vendor. BUDGET 2020 | IN PROGRESS
MSU EXTENSION PARTNERSHIP | MEDIUM | Master Gardener Coordinator for MSU Extension in Leelanau County. Discussions to explore the possibility of expanding into the village. Several Master Gardener Volunteers living within the village limits or in the vicinity and there is a lot of potential for collaboration on public garden-related projects. 2020 Project | INITIATED
JEFFERSON STREET PEDESTRIAN COURT | MEDIUM | Temporary Closure for pedestrian use? UPDATE: Move to 2020 following discussions with businesses and VC. NEW location to be proposed. | IDLE
PEDESTRIAN SEATING AREAS DOWNTOWN | MEDIUM | $8,000 Allocated to downtown furniture and bike racks for pedestrian comfort. This will follow an evaluation of the finalized TAP project to determine locations. | IDLE
PAVING PROJECT PARK WALKWAY | MEDIUM | South Shore/Suttons Park - create pedestrian circulation, reclaim park from parking area. Angle 20-23 ft. UPDATE: Elmer's proposal recommended to Village Council. UPDATE: Proposal signed - awaiting timing of project. | INITIATED
CHARTER CABLE EXTENSION DPW | MEDIUM | Discussions with Charter on expanding service to the DPW to properly service the WWTP, offices, etc. UPDATE: Charter measured distance 9-19. waiting on cost and timeframe. | CONTRACT COMPLETE
DPW/WWTP CAMERAS | MEDIUM | Researching 50/50 grant | IDLE
VILLAGE WIFI | MEDIUM / LOW | Met with the GTB regarding WIFI for our residents 7-22-19. A proposal is forthcoming. | INITIATED
PAINT BATHROOMS @ DUESTER PARK | MEDIUM / LOW | Exterior of building needs attention UPDATE- Requested to be initiated again on 7-17-19 Update; postponed due to seiche actions. | COMPLETE
BAHLE PARK TREE EVALUATION | MEDIUM / LOW | General Committee at their 9-3-19 meeting has indicated this is a priority. Staff evaluated trees per committee. UPDATE - Duester Park tree cutting quote received. Dangerous tree quote received 10-7-19 dated same. Project completed per estimates. | COMPLETE
DEUSTER PARK SOCCER | MEDIUM / LOW | Met with Suttons Bay Schools Coach and Leelanau Soccer Club representative regarding the continued use of Deuster fields and upgraded bathrooms. UPDATE: Verbal agreement regarding a partnership with Leelanau Soccer Club & Suttons Bay School for use of park bathrooms. | COMPLETE
DEUSTER PARK DOORS | MEDIUM / LOW | Bathroom doors are damaged - Door knobs do not comply with ADA requirements. UPDATE: 11-25-19 Door initiative taken over- being re-measured 11-25-19. UPDATE 11-27-19 Doors being ordered in January due to budget. | COMPLETE
PORT SUTTONS MAINTENANCE AGREEMENT | MEDIUM / LOW | Still learning about this subject | IDLE
GIS- SHP FILES FROM LEELANAU COUNTY | MEDIUM / LOW | Need this information to build the GIS - UPDATE- F&V obtaining SHP files for Village and Township. Study of lakefront districts to be studied early 2020. | COMPLETE
LAKEFRONT LOT SIZE STUDY | MEDIUM / LOW | COMPARE LOT SIZES / VARIANCE REQUESTS / CONSTRUCTION DATES TO DETERMINE IF ANOTHER DISTRICT OR DIMENSIONAL VARIATIONS ARE NEEDED. UPDATE: 9-19-19 - UPDATE: Study of lakefront district will occur in January of 2020. | IN PROGRESS
ZONING ORDINANCE | MEDIUM / LOW | The new Ordinance fails to implement "form" as intended. Standards are missing, definitions don’t match terminology etc. Previously a HIGH priority downgraded until training for PC occurs. | INITIATIVE RETRACTED
BAYVIEW ZONING / Development incentives | LOW | This initiative has been retracted until proper training for PC to understand the modifications proposed. | INITIATIVE RETRACTED
MARINA ORDINANCE | LOW | The Marina Ordinance is dated and should be updated to prepare it for granting opportunities. EAST side. We should also look to replace the bathrooms as a part of the grant application. | IDLE
VILLAGE HALL COPIER | LOW | Discussion had with current vendor- Looking elsewhere. UPDATE - Meeting Scheduled for 7-16-19 UPDATE: Moving forward with new copier contract signed 7-23-19 | COMPLETE
STREET CAMERAS | LOW | Researching 50/50 grant | IDLE
FERRY INITIATIVE | LOW | Discussions ongoing with Elk Rapids. An evaluation of the marinas indicate VSB can (physically) accommodate a ferry however Elk Rapids provides larger challenges. UPDATE: DDA to discuss Ferry on 10-9-19. UPDATE: Ferry Presentation before VC- 11-18-19. | IN COMMITTEE
SUTTONS PARK CAMERAS | LOW | Researching 50/50 grant- Grant Submitted 10-3-19 | COMPLETE - APPLIED
POLICY VILLAGE HALL RENTAL | LOW | A sub-committee to discuss this issue will be needed to determine a need or direction. UPDATE: Committee members were looking into this. UPDATE: Study Completed going before General Committee on 11-5-19 | COMPLETE
POLICY - MEMORIALS | LOW | A sub-committee to discuss this issue will be needed to determine a need or direction. UPDATE: :Committee members were looking into this. | IN COMMITTEE
MARINA WETLAND EVALUATION | LOW | Discussions to review and possibly eradicate invasive species. Currently Speaking with ISN. UPDATE: A review has been completed and information provided. | COMPLETE
HARBOR MASTER CONTRACT | LOW | SIGNED 2019 UNTIL JANUARY 2020/ WILL INCREASE IN PRIORITY AS THE YEAR PROGRESSES - UPDATE: Request for increase in pay received 10-2-19. UPDATE: Discussions ongoing. Recommendation to the Personnel Committee for 11-6-19 UPDATE: Contract Signed. | COMPLETE
WWTP OPERATIONS CONTRACT | LOW | SIGNED 2019 UNTIL DECEMBER 2020/ WILL INCREASE IN PRIORITY / EVALUATING STAGE FOR 2 YEAR EXTENSION. UPDATE: 10-2-19 meeting held- informed them that no contract discussion was needed at this time. | IDLE
SHERIFF CONTRACT | LOW | CONTRACT DISCUSSIONS HAVE TAKEN PLACE - UPDATE: -S. Morgan provided the rough draft with the 1-year extension as accepted by LC. | COMPLETE
RAINGARDEN PARTNERSHIP | LOW | Children's House initiative - UPDATE: Maintenance of raingardens scheduled - UPDATE: Maintenance of raingardens complete.. Great initiative! | COMPLETE
TREE PLANTING INITIATIVE | LOW | Sicily Sanford - Citizen Volunteers requested permission to plant trees in partnership with CRA. UPDATE: Initiative scheduled/completed. 400+- trees planted. | COMPLETE
PARKS & REC BYLAWS | LOW | DRAFT CREATED ON HOLD UNTIL ORDINANCE IS ADOPTED.- UPDATE - PC Subcommittee was requested therefore initiative is tabled. | INITIATIVE RETRACTED
SPLIT RAIL FENCE REMOVAL | LOW | Removal of split rail fence on north and south sides of Village Hall. | COMPLETE
CONGRATS! YOU MADE IT THROUGH MY WORK PLAN AND DIDN’T FALL ASLEEP!

## 2020 Work Plan
PROJECT | PRIORITY LEVEL | DESCRIPTION | STATUS
PARKS & RECREATION PLAN | HIGH | Suttons Park & waterwheel plan has been designed and accepted by PC. UPDATE; 9-14-20 Review of former Goals And objectives are progressing. | IN PROGRESS
MASTER PLAN | HIGH | Update the Master Plan / Separate from Joint Master Plan | IDLE
2020 VEHICLE PURCHASE | HIGH | UPDATE: 7-29-20 Vehicle delivered! | COMPLETE
2020 VEHICLE LOGOS | HIGH | Vehicle logos have been proofed and ordered for 4 of the DPW vehicles and one for the Gator. Installation anticipated in the near future. | COMPLETE
VACATION HOME RENTAL ORDINANCE | HIGH | Poorly Drafted - Requires to be re-written. UPDATE: The Michigan Supreme Court has agreed to hear arguments regarding the commercial vs residential use. To date: The appellate courts have continued to view STR's as a commercial use that is prohibited in residential districts. | IDLE
PURCHASE OF FOGGING MACHINE | HIGH | UPDATE: 7-28-20 -Purchased and in use. This will be used to sterilize the DPW facility as well as the Administrative offices. | COMPLETE
BEACH GROOMING | HIGH | UPDATE: 7-28-20 Beach grooming will take place in the next two weeks to avoid a stagnant water concerns. | COMPLETE
S.SHORE DRIVE EMERGENCY | HIGH | 12-12-19 Meeting on site with LCRC on erosion issues and emergency armoring of S.Shore Drive. Agreement signed 1-7-20 - Work has commenced. | COMPLETE
LITIGATION | HIGH | In process detail not available. | IN PROGRESS
HIGH WATER / EROSION Resolution to Gov. | HIGH | Jack O'Malley contacted my office regarding resolution (6-10-20) mailed on behalf of numerous Leelanau County municipalities. No reply from the State. | COMPLETE
HIGH WATER / EROSION COLLABORATION | HIGH | UPDATE- February - Scheduled a meeting and met with surrounding municipalities, Counties and emergency manager. | COMPLETE
NEW LAND DIVISION ORDINANCE | HIGH | Pre-draft Completed on 1-8-20. Review forthcoming. New Applications, approval documents and checklist for applicants to ensure completed applications and procedural understanding. UPDATE: February- Moved to VC for consideration. UPDATE: Canceled due to COVID-19 - UPDATE: 7-30-20 We will be moving forward with the LDA Draft and reschedule. | COMPLETE
STREET CLEANER | HIGH | Pricing equipment to street clean due to high cost of $225/hr. @ 25 hours, Does not include M-22 UPDATE: Modified to include M-22 due to lack of urgency associated with TAP contractor. Pushed back to July 6th due to work load. | COMPLETE
DRAFT NEW ZBA BYLAWS | HIGH | Pre-draft Completed For ZBA Discussion. Provided at the January meeting. | COMPLETE
FIREWORKS ORDINANCE Amendment | HIGH | Ordinance is dated and does not conform to State law. Updates required. UPDATE: Ordinance is now complete due to being pushed back due to COVID-19. Will be provided to committee for consideration in July. UPDATE: 7-9-20 Committee elevated this to VC. | COMPLETE
STREET EVALUATION - SOUTH SHORE | HIGH | UPDATE: 7-9-20 Contract signed with Elmer's to crush and reshape. UPDATE 10-02-20 - Work to begin in October by Elmer's. UPDATE- 10-20-20 - Crush occurred on 10-20-20. Project complete. | COMPLETE
STREET EVALUATION SOUTH SHORE | HIGH | UPDATE: 7-9-20 Contract signed with Elmer's to patch the hump once fixed. KAL will be hired to replace the culvert. UPDATE 10-02-20 - Hump postponed until spring. | IN PROGRESS
BROADWAY STREET | HIGH | UPDATE: 9-14-20 Plan received and will be displayed. 10-02-20. Contract signed project a go for Phase #1. UPDATE: 11/2020- Miss Dig Complete. | IN PROGRESS
CROSS CONNECTION ORDINANCE | HIGH | MDEQ REQUIREMENT | IDLE
ZONING MAP | HIGH | Adopted Zoning Map is incorrect and requires an amendment. Update: Planning Commission Scheduled a Public Hearing (3-11-20) UPDATE: Village council adopted change in June. New Map has been created. | COMPLETE
CONSUMERS ENERGY GRANT | HIGH | This is a high level priority due to time constraints. Application has been submitted 2-26-20 to create a Hydro Charge Park. H20-power for EV charging stations. Not Selected. | COMPLETE
MARINA BOAT LAUNCH CLOSURE | HIGH | DUE TO HIGH WATER AND SAFETY CONCERNS ASSOCIATED WITH THE MARINA LAUNCH WE ARE EVALUATING IT FOR CLOSURE. UPDATE See Report VSB-2020-06 Update: VC Agenda for 2-17-20 - VSB 2020-13- Temporarily CLOSED | COMPLETE
MARINA PARK CLOSURE TO FESTIVALS | HIGH | Committee to discuss the closure of Marina Park to festivals / Mass Gatherings | COMPLETE
EMPLOYEE RETIREMENT LEGAL ISSUE | HIGH | An Attorney has been retained to address issues regarding the Village retirement accounts. UPDATE: February- Conference calls with Attorneys and KDP. Direction for resolve provided. Ongoing issue, however, we are on the right track to resolve issue without litigation. 401 vs 403 | COMPLETE
TAP PROJECT | HIGH | UPDATE: 7.30.20. Paving sub-contractors "fix" needs to be fixed again as do some concrete issues. A second "final" walkthrough is forthcoming. | COMPLETE
STREET EVALUATION - ELM STREET | HIGH | UPDATE: 7.30.20 collaboration has begun. UPDATE 9-14-20: Met last week with Elmer's on site with DPW Director. UPDATE: 10-01-02 - Proposal to go before VC for consideration and budget consideration (2021 summer project). CONTRACT SIGNED. | COMPLETE
NORTH PARK BATHROOM UPGRADE | HIGH | Replace faucets with "timed" faucets and replace counters. Both faucets broken and counters rotted. UPDATE: Faucets ordered. UPDATE: 7-30-20 Timed faucets have been installed, counter tops will be an offseason project. | COMPLETE
INLAND SEAS LEASE AGREEMENT | HIGH | 8-24-20 - Draft lease agreement complete and being reviewed by Harbor Master. UPDATE: 9-1-20 Draft Lease agreement emailed to ISEA for review. UPDATE: 10-02-20 response received will evaluate. Update: 11/2020 Discussion on going making progress. | IN PROGRESS
LAKEFRONT LOT SIZE EVALUATION | HIGH | UPDATE: 7-30-20 - To be presented at the August PC meeting. A draft has been provided to the PC for evaluation, comments and questions. August: Walking tour of properties took place. UPDATE: Residents concerned with possible changes. Door to door survey to be performed by PC members and does not support a change. Report forthcoming. | COMPLETE
STREET TREES | HIGH | UPDATE: 6-18-20 - Various trees identified for removal. Next step: contact / contract with tree removal company. Various street trees have been identified and appear to have been ignored for years. Tree company has been contacted, UPDATE: Contract signed to remove / trim 9 trees. Trees removed. | COMPLETE
WATER RESERVOIR EXPANSION | MEDIUM / HIGH | Per MDEQ additional water storage is REQUIRED - this item was recommended by the MDEQ in 2018. UPDATE: F&V reviewing financials and eligibility for granting opportunities. UPDATE: Met with F&V to discuss expansion initiative. 40 year loan @ 2.5%(ish) on $2.5 million loan would cover line upgrade northern loop, reservoir, and 2 new wells. Next steps forthcoming. See rate note below. | IN PROGRESS
WATER RATES | MEDIUM / HIGH | EVALUATION OF WATER RATES UPDATE: F&V UPDATE: Reviewing UPDATE: Met with F&V to discuss expansion initiative. RATES would see less than $4.00 / month increase for reservoir expansion etc. listed above to cover that project for life of loan. | IN PROGRESS
WATER WELL PROTECTION GRANT | MEDIUM / HIGH | Grant secured by EGLE. Step #2 is to create a new program. | COMPLETE
WATER WELL PROTECTION PROGRAM | MEDIUM / HIGH | UPDATE: 7-30-20 Grant submitted. UPDATE: 10-01-20 - New program completed and submitted. | COMPLETE
ZONING FENCE AMENDMENT | MEDIUM / HIGH | Section 2-21 of the VSB zoning ordinance requires clarification and clarity. | INITIATED
MARINA BRIDGE | MEDIUM / HIGH | UPDATE: Bridge removed | COMPLETE
ARCHITECT - ADA COMPLIANT DECK | MEDIUM / HIGH | Funding retracted by committee. All involved have been notified that project is a no go. No further action to be taken without full VC direction by motion. To be removed for 2021 | INITIATIVE RETRACTED
VILLAGE WATER ORDINANCE | MEDIUM / HIGH | This item has been recommended by the MDEQ in 2018 - Ordinance dated needs attention - F&V to review and provide direction. Contract needed | INITIATED
GPS SERVICES | MEDIUM | There have been several discussion with the vendor working towards a free 30-60 day unit and service. - Wil meet in fall to continue discussions. - UPDATE: Trial period accepted by vendor. BUDGET 2021 | IDLE
MSU EXTENSION PARTNERSHIP | MEDIUM | UPDATE: Email exchange on 7-28-20 - The Village was asked to identify areas that could benefit from this partnership to begin discussions. UPDATE: 8-2020 MSUE representative is evaluating the sites identified. UPDATE: 10-01-20 - Project agreements submitted - partnership initiated. | COMPLETE
JEFFERSON STREET PEDESTRIAN COURT | MEDIUM | Temporary Closure for pedestrian use? UPDATE: NEW location to be proposed (trailer parking) following TAP project? | INITIATIVE RETRACTED
PEDESTRIAN SQUARE INITIATIVE | MEDIUM | Boat trailer parking area to be temporarily used as a seating and viewing area. This initiative will replace the Jefferson Street Pedestrian Court initiative. UPDATE: 3-3-20 Meeting with DPW Staff to brainstorm ideas. UPDATE: May 2020: seating area created in trailer parking area &Grove road end. | COMPLETE
PEDESTRIAN SEATING AREAS DOWNTOWN | MEDIUM | $8,000 Allocated to downtown furniture and bike racks for pedestrian comfort. This will follow an evaluation of the finalized TAP project to determine locations. | COMPLETE
WATERWHEEL PARK | MEDIUM | UPDATE: Plans displayed. UPDATE: Discussion on how the VC wants to proceed is required. A new waterwheel, new waterwheel infrastructure, relocating stream, etc. is estimated at nearly $500,000. UPDATE: 11/2000 Spring upgrade of the area next to Haystacks to be implemented. | IN PROGRESS
VILLAGE STREET -WEIGHT LIMITS | MEDIUM | Vehicles with excess weight damaging Village Streets. Weight limits on numerous roadways including Elm to circumvent unnecessary weight and short cuts by semi-trucks. UPDATE: 9/19 Meeting scheduled with LCRC. | IDLE
PAVING PROJECT - PARK WALKWAY | MEDIUM | South Shore/Suttons Park - create pedestrian circulation, reclaim park from parking area. Angle 20-23 ft. | INITIATED
2% GRANT PARTNERSHIP | MEDIUM | A successful 2% grant application. Looking forward to this partnership with the GTB. | COMPLETE
CHARTER CABLE EXTENSION DPW | MEDIUM | Discussions with Charter on expanding service to the DPW to properly service the WWTP, offices, etc. UPDATE: Charter measured distance 9-19. waiting on cost and timeframe. | COMPLETE
DPW/WWTP CAMERAS | MEDIUM | Researching 50/50 grant UPDATE: Resolution before VC in November. | INITIATED
US BR 35 RE-ROUTE | MEDIUM | Application complete - See VSB-2020-05 UPDATE: VC consideration 2-17-20 UPDATE: MDOT has reviewed the request and is recommending the change to AASHTO. Change adopted. | COMPLETE
RAINGARDENS | MEDIUM | Downtown raingardens have been improved. Remaining raingardens to be evaluated for improvement / removal in Spring. UPDATE: An adopt a raingarden initiative will be reinitiated in the spring. | COMPLETE
INTERGOVERNMENTAL AGREEMENT SEWER & WATER | MEDIUM | Intergovernmental agreement for water & sewer services outside of Village limits is in need of review and re-drafting. | INITIATED
VILLAGE WIFI | MEDIUM / LOW | Met with the GTB regarding WIFI for our residents 7-22-19. A proposal is forthcoming. UPDATE: 10-01-20 - Discussions with GTB representatives have been re-initiated. | INITIATED
PORT SUTTONS MAINTENANCE AGREEMENT | MEDIUM / LOW | Still learning about this subject | IDLE
GIS- SHP FILES FROM LEELANAU COUNTY | MEDIUM / LOW | Need this information to build the GIS - UPDATE- F&V obtaining SHP files for Village and Township. Study of lakefront districts to be studied early 2020. | COMPLETE
VIKING CRUISE LINES | MEDIUM / LOW | Discussion at the sub-committee meeting recommended further discussion. UPDATE; 7-30-20- A meeting is anticipated to discuss Vikings intent and desires. UPDATE:11/2020 Viking discussion was positive and further discussions scheduled. | IN PROGRESS
ZONING ORDINANCE | MEDIUM / LOW | Minor amendments to the ordinance have been discussed. UPDATE: 10-02-20- Various changes moving forward. | IN PROGRESS
VISITOR BATHROOMS | MEDIUM / LOW | New bathrooms for year round use? Committee did not feel it was a Village goal at this time. | COMPLETE
DOWNTOWN BANNER POLICY | MEDIUM / LOW | Downtown banners require compliance with MDOT regulations. Village policy may be necessary to ensure oversight. | IN PROGRESS
BAYVIEW ZONING / Development incentives | LOW | UPDATE: August Letter sent to all PUD owners .UPDATE 10-01-20 - 3 of 4 property owners have shown interest. All owners needed for Village initiative. Project retracted until further cooperation is obtained. Initiative complete. | COMPLETE
MARINA MASTER PLAN REVIEW | LOW | Review of the Marina Master Plan is near complete and will be updated in 2021. | IN PROGRESS
SUTTONS PARK CAMERAS | LOW | GRANT AWARDED - UPDATE: 6-24-20 Met onsite with contractor to determine an implementation strategy and timeframe. UPDATE: 7-29-20 - New pole installed, cable installed, now awaiting camera installation. | COMPLETE
M-22 DOWNTOWN STREET CAMERAS | LOW | UPDATE: 11-10-20 - Installation may still occur in 2020. | INITIATED
BAHLE HUT PARK TREE HARVESTING | LOW | Tree cutting or harvesting to be discussed to widen the sledding hill. | IDLE
FERRY INITIATIVE | LOW | Initiative postponed. | POSTPONED
ICE RINK PARK | LOW | Discussions on park partnership have not materialized. Village has questioned if the Township would like to relinquish the park to Village. UPDATE: 7-30-20 - -This subject remains idled and will be removed from the 2021 work plan. | IDLE
POLICY - MEMORIALS | LOW | A sub-committee to discuss this issue will be needed to determine a need or direction. UPDATE: :Committee members were looking into this. | IDLE
LAW ENFORCEMENT CONTRACT | LOW | Agreement reached on 2021 not to exceed contract. Thank you Steve Morgan for your continued professionalism in working with the Village. | COMPLETE
WWTP OPERATIONS CONTRACT | LOW | 8-25-20 Contract extension of 1 -year has been signed by both parties for 2021. | COMPLETE

## 2021 Work Plan
PROJECT | PRIORITY LEVEL | DESCRIPTION | STATUS
PARKS & RECREATION PLAN | HIGH | Suttons Park & waterwheel plan has been designed and accepted by PC. UPDATE; 9-14-20 Review of former Goals And objectives are progressing. | IN PROGRESS
MASTER PLAN | HIGH | Update the Master Plan / Separate from Joint Master Plan | IDLE
ELM STREET ROADWAY | HIGH |  | IN PROGRESS
ELM STREET CULVERT FUNDING | HIGH
VIKING CRUISE LINES | HIGH
M-DOT PARTNERSHIP M-22 / M-204 | HIGH
FEMA - FIRM MAP | HIGH
VACATION HOME RENTAL ORDINANCE | HIGH | Poorly Drafted - Requires to be re-written. UPDATE: The Michigan Supreme Court has agreed to hear arguments regarding the commercial vs residential use. To date: The appellate courts have continued to view STR's as a commercial use that is prohibited in residential districts. | IDLE
SEWER / WATER INTERGOVERNMENTAL AGREEMENT | HIGH
SANITARY SEWER FIX | HIGH
NO PARKING ORDINANCE | HIGH | Amend the appropriate ordinance to disallow the parking of boats / trailers unattached from vehicles in our roadway.
LITIGATION | HIGH | In process Detail not available. | IN PROGRESS
PLOW TRUCK | HIGH
M-22 SIDEWALKS | MEDIUM / HIGH
PLOW TRUCK WING | MEDIUM / HIGH
SALT STORAGE BARN | MEDIUM / HIGH
DPW CAMERA GRANT | MEDIUM / HIGH
DOWNTOWN STREET LIGHTS | MEDIUM / HIGH
MEDIUM
MEDIUM
MARINA BRIDGE REPLACEMENT | MEDIUM
MARINA MASTER PLAN | MEDIUM / LOW | The Marina Ordinance is dated and should be updated to prepare it for granting opportunities. EAST side. We should also look to replace the bathrooms as a part of the grant application. | INITIATED
DOWNTOWN WATER FOUNTAIN | MEDIUM / LOW
PARK WATER FOUNTAINS | MEDIUM / LOW
MEDIUM / LOW
MARINA WALKWAY REMOVAL | MEDIUM / LOW
BAHLE HUT PARK TREE HARVESTING | LOW | Tree cutting or harvesting to be discussed to widen the sledding hill. | IDLE
ADOPT-A-RAINGARDEN | LOW
ADOPT-A-BASIN | LOW
PARK BENCHES | LOW
ICE RINK PARK | LOW | Discussions on park partnership have not materialized. Village has questioned if the Township would like to relinquish the park to Village. This subject remains idled however the parcel would be ideal for a dog park (if desired) in the spring/summer/fall months and ice rink in winter. | IDLE
POLICY - MEMORIALS | LOW | A sub-committee to discuss this issue will be needed to determine a need or direction. UPDATE: :Committee members were looking into this. | IDLE